## Slide 1
Documentation, Record Keeping & Stewardship
Global Grant Project Management
Deepak Rajbhandary | RC Himalayan Golfers
District 3292 Stewardship Sub Committee | 2026-27
May 29, 2026
ROTARY DISTRICT 3292
PAGE 01

## Slide 2
DEFINING STEWARDSHIP
ROTARY DISTRICT 3292
PAGE 02
What is Stewardship?
In Rotary, stewardship is the thorough, responsible, and ethical management of items or funds entrusted to our care. It ensures that donor funds are used exclusively for their intended purposes.
Accountability to donors
Operational transparency
Compliance with TRF policies

## Slide 3
GOVERNANCE: APPROVALS & GG NUMBERS
ROTARY DISTRICT 3292
PAGE 03
Yearly Approvals
Ensure all club approvals are in place Every Year. Authorization is not a one-time event; it must be maintained.
GG Number
Global Grant number must be obtained before any project activities commence. Do not start without it.
MOU Execution
Host and International clubs must sign the MOU yearly. If a cooperating agency is involved, a 3-party MOU is required.

## Slide 4
GOVERNANCE: KEY CONTACTS
ROTARY DISTRICT 3292
PAGE 04
Primary & Secondary Contacts
Every grant must have a clear hierarchy of accountability:
Submission Timeline
Online applications must be signed by the President (P) and President-Elect (PE) within 6 months of getting a GG Number.
Primary Contact: Holds the ultimate responsibility for project integrity and reporting.
Secondary Contacts: Must be identified at both the Host and International clubs.

## Slide 5
PROJECT & FINANCIAL PLAN
ROTARY DISTRICT 3292
PAGE 05
Strategic Alignment
A successful Global Grant starts with a robust financial plan aligned with the grant application. Do not exceed budget line items.
Phase | Action Requirement
Before Project Starts | Finalize Financial Plan and Budget line items.
Implementation | Track documentation against the approved plan.
Start Deadline | Project must start within 12 months of approval.

## Slide 6
COMMUNITY NEEDS ASSESSMENT
ROTARY DISTRICT 3292
PAGE 06
The Baseline Assessment
Every project must be based on a verified community need, not club assumptions.
Required Metrics
Measuring Basis: How are you quantifying the need?
Beneficiaries: Exactly how many people will benefit?
Sustainability: How will the community maintain the project?
Conflict of Interest: Declare any potential issues upfront.

## Slide 7
FINANCIAL RESPONSIBILITIES: BANKING
ROTARY DISTRICT 3292
PAGE 07
The Dedicated Account
Funds for each GG must be kept in a separate dedicated bank account.
Account Name format: Club Name, GG Number/Project Name
Interest & Compliance
Account must be low or non-interest bearing.
Interest Rule: Interest earned can only be used with prior written TRF approval.
Open account as soon as GG is approved, before funds arrive.

## Slide 8
EXPENDITURE & DISBURSEMENT SOP
* All grant-related inflows/outflows MUST go through the dedicated GG account.
ROTARY DISTRICT 3292
PAGE 08
Control Area | Mandatory Procedure
Verification | All expenses must be documented with original receipts and bank statements.
Bid Process | Compulsory bid process for vendors to ensure best value and transparency.
Signatories | Two designated authorized members + President (or alternate).
Independence | Person who selects the vendor cannot be involved in payment.

## Slide 9
INTERNAL CONTROLS: PAYMENT METHODS
ROTARY DISTRICT 3292
PAGE 09
Monthly Reconciliation: Reconcile bank statements monthly against the ledger. Entries must be made by the Treasurer or an alternate as recorded in the Financial Plan.
Standard Method
Payments must be made by cheque or bank transfer. This provides an immutable audit trail.
Exception Case
Cash payments are only allowed where no banking system exists, and require Prior TRF Approval.

## Slide 10
BEST PRACTICES: FINANCIAL INTEGRITY
ROTARY DISTRICT 3292
PAGE 10
Exchange Rates
Use only the official RI exchange rate. Apply the conversion rate on the exact day of the transaction.
Cash Vouchers
Use numbered vouchers for cash. Must be signed by the Payee and a Witness.
Disclose Interest
All interest earned must be explicitly disclosed in the final financial report.

## Slide 11
ROTARY PUBLICITY & HANDOVER
ROTARY DISTRICT 3292
PAGE 11
Highlight the Impact
Leadership Continuity
Handover SOP: Proper transfer of continuing grants, details, and documents to the new team/Rotary year leadership is mandatory.
Local Media: Feature project in radio, TV, and newspapers.
Identification: Use stickers and banners on all project items.
Ceremony: Ensure high visibility at closing ceremonies.

## Slide 12
RISK MANAGEMENT: RED FLAG INDICATORS
ROTARY DISTRICT 3292
PAGE 12
What NOT to do
Late Reporting
Notice is sent 1 month prior. Final report is due within 2 months of completion.
•
Mixing grant money with any other personal or club account.
•
Using funds for expenses not listed in the grant approval.
•
Fictitious expenses or forged signatures.
•
Financial statements that do not balance with the ledger.
•
Poor quality products that don't meet sustainability goals.

## Slide 13
THE "80% RULE" FOR DISTRICTS
ROTARY DISTRICT 3292
PAGE 13
80%
District Qualification
The District must retain a minimum of 80% clearance of all grants. If reporting drops below this, the entire District can be disqualified from receiving new Global Grants.
Result: Clubs will be unable to start any new Global Grant projects.

## Slide 14
CONSEQUENCES OF MISMANAGEMENT
ROTARY DISTRICT 3292
PAGE 14
Misuse of Funds
Club and District disqualification. If guilty, RI may terminate the member involved.
TRF Refunds
The Rotary Foundation (TRF) will demand a full refund of mismanaged or undocumented funds.
Legal Action
Severe misuse can lead to formal legal recourse and permanent suspension from future grants.

## Slide 15
RETENTION PERIOD: THE 5-YEAR RULE
All Global Grant records must be retained for 5 Years.
ROTARY DISTRICT 3292
PAGE 15
Financial Records
Grant Administration
•
Original bank statements & invoices.
•
Receipts, bills, and bid documents.
•
Currency exchange receipts.
•
Exception approvals (for cash).
•
Approved applications & MOUs.
•
Meeting minutes & TRF approvals.
•
All legal correspondences.
•
Sustainability and implementation plans.

## Slide 16
HOW TO KEEP PHYSICAL RECORDS
ROTARY DISTRICT 3292
PAGE 16
The Gold Standard for Archives
Security: Safe, locked locker known to only a few responsible officers.
Organization: Separate binders for every single grant number.
Originals: Never lend out original documents; they must stay in the club archive.

## Slide 17
DIGITAL STEWARDSHIP SYSTEMS
ROTARY DISTRICT 3292
PAGE 17
Modern Record Keeping
Develop a robust system for digital redundancy:
Backup: Use cloud storage (OneDrive/Google Drive) per grant.
Scanning: Scan all documents to PDF immediately upon receipt.
Photos: Maintain a photo log for the final report.

## Slide 18
REPORTING WORKFLOW ON MY ROTARY
ROTARY DISTRICT 3292
PAGE 18
Path: Go to My Rotary → My Grants → Click Submit Report (Progress or Final).
All reports must be approved by both Host and International club contacts.
Caution: Save frequently. The system may timeout if you take a break.
Always Submit and Confirm to ensure it reached TRF.

## Slide 19
SUMMARY: WHY STEWARDSHIP MATTERS
ROTARY DISTRICT 3292
PAGE 19
The Stakes are High
Besides suspension, refunds, and legal recourse, poor stewardship means no future grants for your club or district.
The ultimate losers are the future beneficiaries who miss out on critical humanitarian help.

## Slide 20
Q & A
Thank you for your attention and commitment.
ROTARY DISTRICT 3292
PAGE 20
Deepak Rajbhandary
RC Himalayan Golfers | District 3292
Stewardship Sub Committee (2026-27)